## Current Iteration
|  | Iteration Number: |  |  |  | 5
|  | Expected Total effort: |  |  |  | 425
|  | Days In Sprint: |  |  |  | 5
Burndown Chart
User Stories |  | Days (Points Completed) | [6 empty] | Remaining
Product Backlog Items | Total Effort | 1 | 2 | 3 | 4 | 5 | Task Balance | Percentage Completed
Developer will setup & configure SharePoint in online. | 6 | 5 | 2 | 0 | 0 | 0 | -1 | 116.7%
Visitors will be able to view the home page to collect their respective information | 80 | 17 | 18 | 17 | 15 | 13 | 0 | 100%
University contact details will be provided on the website. | 33 | 22 | 11 | 0 | 0 | 0 | 0 | 100%
Visitors will be able to post inquiries on the website. | 64 | 0 | 12 | 20 | 21 | 11 | 0 | 100%
Visitors will be able to university’ s news on the website. | 103 | 27 | 23 | 25 | 19 | 11 | -2 | 101.9%
The website will offer courses for future student. | 43 | 20 | 18 | 5 | 0 | 0 | 0 | 100%
About us page will be available for the visitors to know about the university. | 34 | 0 | 0 | 12 | 18 | 4 | 0 | 100%
Research article of the university will be available for the visitors on the website. | 35 | 18 | 14 | 3 | 0 | 0 | 0 | 100%
Alumni Success Stories will be viewed on the university’s website. | 27 | 0 | 2 | 14 | 11 | 0 | 0 | 100%
Effort Remaining | 425 | 316 | 216 | 120 | 36 | -3 | -3 | 100.7%
Ideal Trend | 425 | 340 | 255 | 170 | 85 | 0
Note on G4: For an Accurate Burndown Chart and Ideal Trend, Fill in the expected working days in an Iteration (1 Week = 5 Days). You can additionally choose to hide columns that are not needed. If your Iteration is 2 weeks long, you can hide columns M through V and place 10 in this box. Default Formula Assumes 20 days